PictureBuild System

Jobs — Training Guide

A complete walkthrough of every feature in the Jobs module.

How to open it:  click "Jobs" in the left menu   (web address: /jobs)

Audience:  All staff — step-by-step, end-user instructions.

Contents

Jobs is the operational hub of PictureBuild — every project from contract to completion. Each job tracks its info and assignments, schedule, work orders, crew time, daily field logs, tasks, change orders, finances (invoices/payments), and files.

# 1. Overview

The page is split into a **job list** on the left and the selected job's content on the right. The list groups jobs by pipeline stage and can be filtered by status, role, and stage.

Note: The ⚙️ Settings tab is admin / super-admin only. All other tabs are visible to everyone, though some data can be limited by your account permissions (set in HR ▸ Permissions).

# 2. The Job List

## 2.1 Status, search & stages

- Open / Closed toggle at the top switches which jobs you see (Open = active or on-hold; Closed = completed or cancelled).

- Search jobs… finds a job by name or client.

- Jobs are grouped into collapsible pipeline stages; All Jobs (pinned at top) shows schedule, tasks, finance, etc. across every job.

- Each row shows the job/client name, the supervisor's initials in parentheses, and a blue Move to stage arrow. Hover for address and phone.

## 2.2 Filter

Click **Filter** to show only jobs where a chosen employee holds a chosen **role** (e.g. Job Supervisor), and/or to **Hide stages**. Use **Clear all** then **Done** to reset.

# 3. Creating a Job

Open the New Job form (sold bids open it automatically). Fields:

| Field | Required | Type / Options | Notes |
| --- | --- | --- | --- |
| Opportunity Name | Yes | Text | The client/opportunity name. |
| Job Address | Yes | Text |  |
| Contract Price | Yes | Number ($) |  |
| Salesperson | No | Text |  |
| Date Sold / Start Date / Est. Completion | No | Date | Date Sold defaults to today. |
| Status | No | Active / On Hold / Completed / Cancelled | Defaults to Active. |
| Notes | No | Textarea |  |

Under **Projects & Modules**, add a **Project** (name + type) and one or more **Modules** (module name, crew type, est. man-days, est. material cost). Click **Create Job** — you're taken to the new job.

# 4. Working a Job — the Tabs

| Tab | What it's for |
| --- | --- |
| ℹ️ Info | Job details, site access, client details, and role assignments. |
| 📅 Schedule | Calendar of scheduled items; Add Schedule, Exceptions, Schedule Assistance. |
| 📋 Work Orders | Work orders for the job. |
| 🎯 Tracking | Cost-vs-estimate tracking. |
| ⏱️ Time Clock | Crew time records. |
| 📝 Daily Logs | Field daily logs. |
| ✅ Tasks | The job's task list. |
| 🔄 Change Orders | Add and manage change orders. |
| 💰 Finance | Invoices, Payments, and Material Costs (from QuickBooks). |
| 📁 Files | Documents and Photos / Videos, organized in folders. |
| ⚙️ Settings | Admin-only configuration (see section 9). |

# 5. Info & Assignments

## 5.1 Edit job details

- Open the job → ℹ️ Info → Job Details → click Edit.

- Update Main Details (status, name, address, contract price, permit #), Site Access (gate code, dog on premises, access notes), and Client Details.

- Click Save.

Note: Quick-assign the responsible person from the top of the Info panel: click the Assigned to field, type a name, and pick it — it saves immediately and the initials show on the job row.

## 5.2 Role assignments

On the **Assignments** sub-tab, click **Edit**, then type an employee into each role and **Save**. The nine roles are: Job Supervisor, Consultant, Design Review, Final Review, Permit & Engineering Coordinator, Production Manager, Quality Control Supervisor, Finance Manager, Success Supervisor.

# 6. Scheduling

- Open the job → 📅 Schedule → Add Schedule, fill in the item, and save.

- Use Exceptions to manage scheduling exceptions (a badge shows the count).

- Use ✨ Schedule Assistance to auto-optimize: first Geocode pending jobs, then pick a mode (Supervisor Assignment, Yard Checks, Warranties, or both), configure start location/dates, review, and click Apply.

# 7. Tracking Costs

- Open the job's detail page and click 📊 Open Job Tracker.

- In Module Breakdown, click Log Entry on a module.

- Enter Date, Man Days Worked (1 MD = 8 hrs), Material Cost, and notes; click Save Entry.

- The GP summary tiles and progress bars update immediately.

# 8. Finance & Files

- 💰 Finance → Invoices → + Add Invoice → choose Progress Invoice or Manual Invoice.

- Payments → + Payment records a payment.

- Material Costs is read-only and flows in from QuickBooks.

- 📁 Files → choose 📄 Documents or 📸 Photos / Videos → + Upload…; use + Add Folder to organize; a file's ⋯ menu offers Rename, Download, Open, Copy to…, and Move to….

# 9. Settings (admin only)

The ⚙️ Settings tab holds: **General** (default schedule color, payroll week, invoice communication position), **Job Stages** (reorder/rename/add/delete), **Task Lists** (categories + descriptions), **Scheduling Assistance** (start locations + supervisor positions), **Job Templates**, **E-Mail Templates**, and **Master Crews**.

# 10. Tips & Best Practices

- Keep each job's stage current — the list grouping and filters depend on it (drag a job onto a stage, or use the Move to stage arrow).

- Fill in Assignments so the right initials show and the role filter works.

- Log actual man-days and materials in the Job Tracker as work happens — that's what makes the GP numbers real.

- Use folders in Files to keep documents and photos tidy per job.

- Run Schedule Assistance after geocoding to balance supervisor load and route yard checks efficiently.

# 11. Where to get help

See the other guides in Help ▸ Documentation, or contact your PictureBuild administrator.